## Scope Matrix
GEO OS · G0-01 Scope Matrix V1.0 | GEO OS · G0-01 Scope Matrix V1.0 | GEO OS · G0-01 Scope Matrix V1.0 | GEO OS · G0-01 Scope Matrix V1.0 | GEO OS · G0-01 Scope Matrix V1.0 | GEO OS · G0-01 Scope Matrix V1.0 | GEO OS · G0-01 Scope Matrix V1.0 | GEO OS · G0-01 Scope Matrix V1.0 | GEO OS · G0-01 Scope Matrix V1.0 | GEO OS · G0-01 Scope Matrix V1.0 | GEO OS · G0-01 Scope Matrix V1.0 | GEO OS · G0-01 Scope Matrix V1.0 | GEO OS · G0-01 Scope Matrix V1.0 | GEO OS · G0-01 Scope Matrix V1.0 | GEO OS · G0-01 Scope Matrix V1.0
Gate 状态：OPEN / PENDING REVIEW · Scope、MVP、权威来源、验收与负责人矩阵 | Gate 状态：OPEN / PENDING REVIEW · Scope、MVP、权威来源、验收与负责人矩阵 | Gate 状态：OPEN / PENDING REVIEW · Scope、MVP、权威来源、验收与负责人矩阵 | Gate 状态：OPEN / PENDING REVIEW · Scope、MVP、权威来源、验收与负责人矩阵 | Gate 状态：OPEN / PENDING REVIEW · Scope、MVP、权威来源、验收与负责人矩阵 | Gate 状态：OPEN / PENDING REVIEW · Scope、MVP、权威来源、验收与负责人矩阵 | Gate 状态：OPEN / PENDING REVIEW · Scope、MVP、权威来源、验收与负责人矩阵 | Gate 状态：OPEN / PENDING REVIEW · Scope、MVP、权威来源、验收与负责人矩阵 | Gate 状态：OPEN / PENDING REVIEW · Scope、MVP、权威来源、验收与负责人矩阵 | Gate 状态：OPEN / PENDING REVIEW · Scope、MVP、权威来源、验收与负责人矩阵 | Gate 状态：OPEN / PENDING REVIEW · Scope、MVP、权威来源、验收与负责人矩阵 | Gate 状态：OPEN / PENDING REVIEW · Scope、MVP、权威来源、验收与负责人矩阵 | Gate 状态：OPEN / PENDING REVIEW · Scope、MVP、权威来源、验收与负责人矩阵 | Gate 状态：OPEN / PENDING REVIEW · Scope、MVP、权威来源、验收与负责人矩阵 | Gate 状态：OPEN / PENDING REVIEW · Scope、MVP、权威来源、验收与负责人矩阵
关闭规则：只有全部范围项具备决策、验收、具名负责人，且 Open Decisions 清零后，才可提交 G0-01 CLOSED 审批。
Scope ID | Type | Domain | Capability / Module | Scope Decision | MVP Level | Delivery Phase | Authority Domain | Primary Authority | Implementation Authority | Acceptance Criteria | Owner Role | Named Owner | Gate / Dependency | Notes / Limitation
MOD-01 | MODULE | Platform | IAM & Tenant | IN | MVP-0 FOUNDATION | Gate 0 / Foundation | Technical structure | Technical Architecture Reconciliation V1.1 | G0-02 Domain Contract + ADR/API/Schema | 受控开通 Tenant；成员、角色和租户上下文可执行；跨租户访问被拒绝并留审计。 | Platform & Security Lead | TBD before G0-01 close | G0-02 | 不包含自助注册、代理层级、白标、计费和开放 API。
MOD-02 | MODULE | Core Platform | Customer / Brand / Project | IN | MVP-1 WALKING SKELETON | Walking Skeleton | MVP scope & acceptance | GEO_OS_需求方案定稿版_V1.0 | Technical Architecture V1.1 + Domain Contract | Tenant Admin 可创建自有 Customer、Brand、Project；对象归属固定且可审计。 | Core Domain Lead | TBD before G0-01 close | G0-02 | Project Policy Binding 只提供默认值。
MOD-03 | MODULE | Contracts | Contract & Policy Release | IN | MVP-0 FOUNDATION | Gate 0 / Foundation | Technical structure | Technical Architecture Reconciliation V1.1 | ADR-008 + Policy Manifest Schema | PolicyDefinition、不可变 PolicyRelease 与实际执行绑定可复现；V1 不建设低代码规则平台。 | Domain Architecture Lead | TBD before G0-01 close | G0-04/G0-06 | Execution、Assessment、Resolution、Snapshot 各自保存实际 policy_release_id。
MOD-04 | MODULE | Demand | Demand & Question | IN | MVP-1 WALKING SKELETON | Walking Skeleton | MVP scope & acceptance | GEO_OS_需求方案定稿版_V1.0 | A1 + QuestionVersion Contract | 至少支持不可变 QuestionVersion、SampleSlot 关联和首行业最小问题分类。 | Demand Domain Lead | TBD before G0-01 close | G0-03 | 完整需求智能在 MVP-2 扩展。
MOD-05 | MODULE | Knowledge | Brand Truth & Evidence | IN | MVP-2 COMMERCIAL COMPLETE | Semantic Expansion | Commercial direction | GEO_OS_产品方案定稿版_V1.0 | Domain Contract + Evidence API | 支持最小 Target/Brand Truth 证据版本供 Pack B 使用；完整知识治理后续补齐。 | Knowledge Domain Lead | TBD before G0-01 close | Pack B | Walking Skeleton 不依赖完整 Brand Truth 平台。
MOD-06 | MODULE | Monitoring | Monitoring & Sampling | IN | MVP-1 WALKING SKELETON | Walking Skeleton | MVP scope & acceptance | GEO_OS_需求方案定稿版_V1.0 | Sampling Contract + Scheduler | QuestionVersion 产生可追踪 SampleSlot；重试不增加 Sample N；计划与执行分离。 | Monitoring Lead | TBD before G0-01 close | G0-05 | 首阶段只支持最小调度能力。
MOD-07 | MODULE | Execution | Query Execution | IN | MVP-1 WALKING SKELETON | Walking Skeleton | Technical structure | GEO_OS_技术方案定稿版_V1.0 | A1 + Execution API/Event | ExecutionRun 保存实际上下文、状态、幂等键与证据引用；失败不自动形成观测。 | Query Platform Lead | TBD before G0-01 close | G0-03/G0-05 | Real AI Query Engine 只负责执行与捕获事实。
MOD-08 | MODULE | Observation | Observation Capture | IN | MVP-1 WALKING SKELETON | Walking Skeleton | Domain semantics | Decision Pack A1/A2/A3 | Observation State Machine + DDL + Contract Tests | 实现 CAPTURING→FINALIZING→FINALIZED；原始事实不可原地修改，错误通过 CorrectionRecord 处理。 | Observation Domain Lead | TBD before G0-01 close | G0-03 | 不得静默重分类或硬删除。
MOD-09 | MODULE | Decisioning | Assessment / Review / Resolution | IN | MVP-1 WALKING SKELETON | Walking Skeleton | Domain semantics | Decision Pack A2/A3/B/C | ADR-005 + Envelope Schema | 通用 Envelope 与领域 Payload 分离；append-only Assessment/Review；Resolution 可确定复现。 | Assessment Domain Lead | TBD before G0-01 close | G0-04 | 禁止万能业务大表与 global latest wins。
MOD-10 | MODULE | Measurement | Measurement & Snapshot | IN | MVP-1 WALKING SKELETON | Walking Skeleton | Domain semantics | Decision Pack A2/A3 | ADR-007 + Snapshot ERD/DDL | Snapshot 冻结 Observation/Metric 两层 Membership、实际 Resolution Provenance 与实际 Policy Release。 | Measurement Lead | TBD before G0-01 close | G0-06 | Walking Skeleton 使用非客户测试指标或冻结的 ANSWER_OUTCOME。
MOD-11 | MODULE | Citation | Citation & Source | IN | MVP-2 COMMERCIAL COMPLETE | Semantic Expansion | Domain semantics | Decision Pack C | Citation/Source Domain Contract + API | 实现 Occurrence、Qualification、LogicalCitation、SourceBinding、Resolution 分层及 Citation Presence 最小链路。 | Citation & Source Lead | TBD before G0-01 close | Pack C / G0-02 | 不得退化为扁平 URL 数组。
MOD-12 | MODULE | Intelligence | GEO Intelligence | DEFERRED | MVP-2 COMMERCIAL COMPLETE | Post Walking Skeleton | Commercial direction | GEO_OS_产品方案定稿版_V1.0 | Open Decision OD-G01-002 | 先消费冻结 Snapshot；策略建议的正式客户验收边界在 G0-01 评审前确认。 | Product Intelligence Lead | TBD before G0-01 close | OD-G01-002 | 不阻塞基础设施和 Walking Skeleton。
MOD-13 | MODULE | Intervention | Intervention & Effect Validation | DEFERRED | MVP-2 COMMERCIAL COMPLETE | Post Walking Skeleton | Commercial direction | GEO_OS_产品方案定稿版_V1.0 | Open Decision OD-G01-003 | 明确干预目录、版本化执行、前后 Snapshot 对比和最小验收边界后进入实现。 | Intervention Lead | TBD before G0-01 close | OD-G01-003 | 不提前冻结复杂策略规则。
MOD-14 | MODULE | Delivery | Report & Delivery | IN | MVP-1 WALKING SKELETON | Walking Skeleton | MVP scope & acceptance | GEO_OS_需求方案定稿版_V1.0 | Snapshot Consumer Contract | Basic Report 只读取指定 Snapshot 并可重复交付；正式客户 KPI 在语义准入后开放。 | Delivery Lead | TBD before G0-01 close | G0-06 / OD-G01-006 | 不得在前端重算正式指标。
MOD-15 | MODULE | Operations | Resource / Cost / Audit | IN | MVP-0 FOUNDATION | Foundation | Technical structure | GEO_OS_技术方案定稿版_V1.0 | Audit/Event/Cost Schema | 关键操作、模型调用、执行成本和管理员跨租户访问均可追踪；经营分析延后。 | Platform Operations Lead | TBD before G0-01 close | G0-02/G0-05 | Redis 不保存唯一业务事实。
X-01 | CROSS-CUTTING | Security | Tenant Isolation | IN | MVP-0 FOUNDATION | Gate 0 / Foundation | Technical structure | Technical Architecture Reconciliation V1.1 | G0-02 ADR + Isolation Contract Tests | API、查询、唯一约束、缓存键、对象路径和队列载荷均声明 tenant scope。 | Platform & Security Lead | TBD before G0-01 close | G0-02 | 第三方仅管理自有客户。
X-02 | CROSS-CUTTING | Identity | GLOBAL_IDENTITY_WITH_TENANT_CONTEXT | IN | MVP-0 FOUNDATION | Gate 0 / Foundation | Technical structure | Technical Architecture Reconciliation V1.1 | Ownership Matrix + Hidden Directory Authorization | 全局目录不直接向租户暴露；Evidence/Binding/Relationship/Projection 通过租户上下文授权。 | Data Architecture Lead | TBD before G0-01 close | G0-02 | 跨租户可去重但不得信息侧漏。
X-03 | CROSS-CUTTING | Security | Authentication & RBAC | IN | MVP-0 FOUNDATION | Foundation | MVP scope & acceptance | GEO_OS_需求方案定稿版_V1.0 | IAM Contract + Authorization Tests | 平台管理员、Tenant Admin、成员和客户只读角色具备明确权限边界。 | Platform & Security Lead | TBD before G0-01 close | G0-02 | 不以 UUID 难猜代替授权。
X-04 | CROSS-CUTTING | Governance | Auditability | IN | MVP-0 FOUNDATION | Foundation | Technical structure | GEO_OS_技术方案定稿版_V1.0 | Audit Event Schema | 敏感访问与状态变更记录 actor、reason、target、tenant、trace 与时间。 | Platform Operations Lead | TBD before G0-01 close | G0-02/G0-05 | 审计记录不可依赖应用日志替代。
X-05 | CROSS-CUTTING | Observation | Immutable Fact Lifecycle | IN | MVP-0 FOUNDATION | Gate 0 / Foundation | Domain semantics | Decision Pack A1/A3 | G0-03 State Machine + DDL | Finalization 原子且幂等；FINALIZED 事实拒绝原地 UPDATE。 | Observation Domain Lead | TBD before G0-01 close | G0-03 | Correction 与 Projection 不修改事实层。
X-06 | CROSS-CUTTING | Decisioning | Resolution Protocol | IN | MVP-0 FOUNDATION | Gate 0 / Foundation | Domain semantics | Decision Pack A2/A3/B/C | G0-04 Envelope + Resolution Tests | 粒度、上下文、证据优先级和冲突状态均可复现。 | Assessment Domain Lead | TBD before G0-01 close | G0-04 | 领域 Payload 保持专用。
X-07 | CROSS-CUTTING | Reliability | Outbox / Inbox / Idempotency | IN | MVP-0 FOUNDATION | Gate 0 / Foundation | Technical structure | Technical Architecture Reconciliation V1.1 | G0-05 Event Contract + Failure Matrix | 业务状态与 Outbox 同事务；重复投递/消费不产生重复事实；重试和租约可恢复。 | Platform Reliability Lead | TBD before G0-01 close | G0-05 | BullMQ/Redis 不是事实来源。
X-08 | CROSS-CUTTING | Measurement | Snapshot Contract | IN | MVP-0 FOUNDATION | Gate 0 / Foundation | Domain semantics | Decision Pack A3 | G0-06 Membership + Replacement Contract | Snapshot 生命周期与完整性正交；错误通过显式 Replacement 链处理。 | Measurement Lead | TBD before G0-01 close | G0-06 | Report 永久绑定交付时 Snapshot ID。
X-09 | CROSS-CUTTING | Contracts | Actual Policy Release Binding | IN | MVP-0 FOUNDATION | Gate 0 / Foundation | Technical structure | Technical Architecture Reconciliation V1.1 | ADR-008 + Binding Contract Tests | 项目默认配置变化不得改写历史 Execution/Assessment/Resolution/Snapshot。 | Domain Architecture Lead | TBD before G0-01 close | G0-04/G0-06 | 实际使用版本必须落库。
X-10 | CROSS-CUTTING | Infrastructure | Object Storage | IN | MVP-0 FOUNDATION | Foundation | Technical structure | GEO_OS_技术方案定稿版_V1.0 | Storage Contract + Integrity Checks | 大对象证据按 tenant/context 路径与 hash 管理；数据库保存不可丢失引用。 | Platform Infrastructure Lead | TBD before G0-01 close | G0-02/G0-03 | 对象上传与 Finalization 失败可恢复。
X-11 | CROSS-CUTTING | Operations | Observability & Trace Context | IN | MVP-0 FOUNDATION | Foundation | Technical structure | GEO_OS_技术方案定稿版_V1.0 | Trace/Log/Event Correlation Contract | 请求、任务、事件和模型调用共享 correlation_id/trace_id 并支持租户级排障。 | Platform Reliability Lead | TBD before G0-01 close | G0-05 | 日志不得泄漏跨租户数据。
X-12 | CROSS-CUTTING | Engineering | Monorepo / CI / Contract Tests | IN | MVP-0 FOUNDATION | Foundation | Technical structure | Technical Architecture Reconciliation V1.1 | Repository Skeleton + CI | TypeScript/Python 工程规范、Lint、单元/集成/契约测试和迁移检查可自动执行。 | Engineering Enablement Lead | TBD before G0-01 close | G0-01 | 非争议部分允许并行启动。
X-13 | CROSS-CUTTING | Data | Database Migrations & Constraints | IN | MVP-0 FOUNDATION | Foundation | Engineering implementation | ADR / Domain Contract | Migration + Schema Tests | 所有 Schema 变更通过迁移；跨租户、幂等、版本与不可变约束有数据库级防线。 | Data Architecture Lead | TBD before G0-01 close | G0-02~G0-06 | Gate 未关闭前不冻结最终核心表。
X-14 | CROSS-CUTTING | Governance | Contract Traceability | IN | MVP-0 FOUNDATION | Gate 0 / Continuous | Engineering implementation | Technical Architecture Reconciliation V1.1 | Traceability Matrix + Contract Test IDs | 正式交付规则可定位到对象、Schema/API/Event、代码和测试；随模块持续补齐。 | Architecture Governance Lead | TBD before G0-01 close | G0-01 | 无需开工前一次填满全部规则。
X-15 | CROSS-CUTTING | Industry | Industry Extension Interface | IN | MVP-1 WALKING SKELETON | Architecture Extension | Technical structure | Technical Architecture Reconciliation V1.1 | Version Reference + No-hardcode Tests | 通用模型禁止行业字段硬编码；Project 可引用首行业规则版本。 | Domain Architecture Lead | TBD before G0-01 close | P0 | 完整 IndustryPolicyPack 在第二行业前冻结。
X-16 | CROSS-CUTTING | Commercial | Third-party Tenant Workspace | IN | MVP-2 COMMERCIAL COMPLETE | Commercial Enablement | Commercial direction | 冻结注释 FZ-01 | Tenant Workspace Acceptance Tests | 平台受控开通第三方 Tenant；第三方管理本机构成员和自有客户。 | Product Owner | TBD before G0-01 close | G0-02 | 不包含代理父子层级、白标、计费、自助注册和开放 API。
X-17 | CROSS-CUTTING | Commercial | Self-service / Agency Hierarchy / White-label / Billing / Open API | OUT | POST-MVP | Not in V1 | Commercial direction | GEO_OS_产品方案定稿版_V1.0 | Future Scope Change Request | V1 不实现；任何提前引入必须作为 MVP 范围变更审批。 | Product Owner | TBD before G0-01 close | Change Control | Tenant Isolation 不等于开放代理商平台。
X-18 | CROSS-CUTTING | Rules | Dynamic Low-code Policy Platform | OUT | POST-MVP | Not in V1 | Technical structure | Technical Architecture Reconciliation V1.1 | Future Architecture ADR | V1 采用版本化 Manifest、不可变 Release 和代码 Evaluator。 | Domain Architecture Lead | TBD before G0-01 close | Change Control | 确有运营动态配置需求后再评估。
X-19 | CROSS-CUTTING | Measurement | Formal Customer Mention / Recommendation / Citation KPI | DEFERRED | MVP-2 COMMERCIAL COMPLETE | After semantic gates | Domain semantics | Decision Pack B/C | OD-G01-006 + KPI Contract | Pack B/C、Coverage Context、资格与贡献规则冻结并通过契约测试后才开放客户指标。 | Measurement Lead | TBD before G0-01 close | OD-G01-006 | Basic Report 阶段禁止提前输出。
X-20 | CROSS-CUTTING | Industry | Full Multi-industry Policy Pack | DEFERRED | POST-MVP | Before second industry | Commercial direction | Technical Architecture Reconciliation V1.1 | IndustryPolicyPack ADR | 第二行业正式实现前冻结依赖、兼容、发布、迁移、停用和回滚机制。 | Domain Architecture Lead | TBD before G0-01 close | P1 | 首行业 + 影子行业先验证无硬编码。
RUN-01 | RUNTIME | Execution | Real AI Query Engine | IN | MVP-1 WALKING SKELETON | Walking Skeleton | Technical structure | GEO_OS_技术方案定稿版_V1.0 | Execution Contract | 独立运行单元负责资源分配、真实端执行、响应检测、捕获与执行证据。 | Query Platform Lead | TBD before G0-01 close | MOD-07 | 不得决定正式语义 KPI。
RUN-02 | RUNTIME | Processing | AI/Data Worker | IN | MVP-1 WALKING SKELETON | Walking Skeleton | Technical structure | GEO_OS_技术方案定稿版_V1.0 | Worker Command/Event Contract | 异步完成抽取、分类、Assessment/Resolution 辅助、Measurement 和报告任务。 | Data Processing Lead | TBD before G0-01 close | G0-04/G0-05 | 不得覆盖 RawObservation。
RUN-03 | RUNTIME | Models | Model Gateway | IN | MVP-0 FOUNDATION | Foundation | Technical structure | GEO_OS_技术方案定稿版_V1.0 | Model Invocation Contract | 记录模型、Prompt/配置版本、成本和调用追踪；不替代真实 Surface 观测。 | Model Platform Lead | TBD before G0-01 close | X-11 | 输出仅作为 Assessment Evidence。
RUN-04 | RUNTIME | Publishing | Publisher Worker | DEFERRED | MVP-2 COMMERCIAL COMPLETE | Post Walking Skeleton | Technical structure | GEO_OS_技术方案定稿版_V1.0 | OD-G01-004 | 明确后续发布适配器与人工辅助流程是否属于 Commercial MVP。 | Publishing Lead | TBD before G0-01 close | OD-G01-004 | V1 不形成独立架构门禁。

## Authority Map
ADR-001 · Authority by Decision Domain | ADR-001 · Authority by Decision Domain | ADR-001 · Authority by Decision Domain | ADR-001 · Authority by Decision Domain | ADR-001 · Authority by Decision Domain
文档权威按决策领域划分，不采用简单全局排名 | 文档权威按决策领域划分，不采用简单全局排名 | 文档权威按决策领域划分，不采用简单全局排名 | 文档权威按决策领域划分，不采用简单全局排名 | 文档权威按决策领域划分，不采用简单全局排名
冲突原则：同一决策领域内，正式冻结 > 草案；范围更具体 > 一般；显式替代且版本更新 > 旧版本。跨领域冲突进入 Change Request。
Decision Domain | Primary Authority | Applies To | Conflict Rule | Escalation / Required Output
Commercial direction | GEO_OS_业务背景定稿版_V1.0 / GEO_OS_产品方案定稿版_V1.0 | 商业目标、目标客户、产品边界、商业模式和路线方向 | 同一领域内：正式冻结 > 草案；范围更具体 > 一般；显式替代的新版本 > 旧版本。 | 冲突无法消解时提交 MVP Scope Change Request。
MVP scope & acceptance | GEO_OS_需求方案定稿版_V1.0 | IN/OUT、优先级、角色权限、功能验收和非功能验收 | 需求方案不得修改 A/B/C 领域语义；语义变化必须进入领域契约变更。 | 更新 Scope Matrix、验收 ID 和 Traceability。
Domain semantics | Decision Pack A1/A2/A3/B/C 最终冻结版 | Observation、Validity、Eligibility、Mention、Recommendation、Citation、Review、Snapshot 等语义 | 最终冻结且更具体的决议优先；技术实现不得以既有代码惯例覆盖冻结语义。 | Breaking Contract Change + 领域批准。
Technical structure | Technical Architecture Reconciliation V1.1 / GEO_OS_技术方案定稿版_V1.0 | 模块边界、运行单元、存储、事件、可靠性、安全和基础设施 | V1.1 对当前工程边界负责；技术方案提供上位技术背景。 | 形成或升级 Architecture ADR。
Engineering implementation | Domain Contract / ADR / API / Schema / Event Contract / Migration / Contract Test | 可执行工程实现与版本 | 必须证明对上位 Scope、领域语义和技术结构的实现，不得反向改写上位决策。 | PR 需要 Traceability 与契约测试。

## Change Control
G0-01 Change Control | G0-01 Change Control | G0-01 Change Control | G0-01 Change Control | G0-01 Change Control | G0-01 Change Control
Change Request → 分类 → 影响评估 → 审批 → 版本升级 → Traceability 更新 → 发布 | Change Request → 分类 → 影响评估 → 审批 → 版本升级 → Traceability 更新 → 发布 | Change Request → 分类 → 影响评估 → 审批 → 版本升级 → Traceability 更新 → 发布 | Change Request → 分类 → 影响评估 → 审批 → 版本升级 → Traceability 更新 → 发布 | Change Request → 分类 → 影响评估 → 审批 → 版本升级 → Traceability 更新 → 发布 | Change Request → 分类 → 影响评估 → 审批 → 版本升级 → Traceability 更新 → 发布
流程阶段
Step | Stage | Required Work | Output | Accountable Role
1 | Change Request | 提交问题、动机、拟议变化、受影响对象和期望时间。 | Request ID + 初始证据 | Requester / PM
2 | Classification | 分类为编辑性、兼容性新增、破坏性契约变更或 MVP 范围变更。 | Change Class | Architecture Governance
3 | Impact Assessment | 评估 Scope、领域语义、API/Schema/Event、数据迁移、历史复现、安全、测试和交付影响。 | Impact Report | Domain + Technical Owners
4 | Approval | 按决策领域路由至产品、领域、技术或项目批准人；破坏性和范围变更不得由单一开发者批准。 | Approval Record | Designated Approver
5 | Version Upgrade | 按分类升级文档、Contract、API/Schema/Event 和 Policy Release 版本。 | Versioned Artifacts | Artifact Owners
6 | Traceability Update | 更新 Scope Matrix、ADR、Rule→Object→Schema/API/Event→Code→Test 映射和 Open Decision。 | Updated Traceability | Architecture Governance + QA
7 | Release | 通过迁移、兼容、回归、契约和回滚检查后发布，并保留 Release Record。 | Release Record | Release Owner
变更分类与版本影响
Code | Class | Definition | Version Impact | Required Approver | Minimum Evidence
EDITORIAL | 编辑性 | 不改变语义、范围、字段含义或行为的文字/排版修正。 | Patch | 文档 Owner | 基础校对；引用/ID 未变化时可不重跑全量契约测试。
COMPATIBLE_ADDITION | 兼容性新增 | 新增可选字段、可选状态、兼容 API 或不影响旧消费者的新能力。 | Minor | 领域 Owner + 技术 Owner | 向后兼容测试、默认行为、Schema/API/Event 版本与 Traceability。
BREAKING_CONTRACT | 破坏性契约变更 | 改变已有语义、必填字段、状态机、唯一约束、历史复现或消费者行为。 | Major | 领域批准人 + 架构批准人 | 迁移/双读写/回滚方案、历史影响、完整契约回归；必要时重开相关 Gate。
MVP_SCOPE_CHANGE | MVP 范围变更 | 改变 IN/OUT/DEFERRED、MVP 等级、验收边界、第三方能力或正式 KPI 准入。 | Scope Baseline Version | Product Sponsor + Project Manager | 商业影响、排期/成本、依赖、验收、风险和 Scope Matrix 全量更新。

## Open Decisions
G0-01 Open Decision Register | G0-01 Open Decision Register | G0-01 Open Decision Register | G0-01 Open Decision Register | G0-01 Open Decision Register | G0-01 Open Decision Register | G0-01 Open Decision Register | G0-01 Open Decision Register | G0-01 Open Decision Register
所有已知冲突必须已解决，或登记具备负责人、期限和关闭产物的 Open Decision | 所有已知冲突必须已解决，或登记具备负责人、期限和关闭产物的 Open Decision | 所有已知冲突必须已解决，或登记具备负责人、期限和关闭产物的 Open Decision | 所有已知冲突必须已解决，或登记具备负责人、期限和关闭产物的 Open Decision | 所有已知冲突必须已解决，或登记具备负责人、期限和关闭产物的 Open Decision | 所有已知冲突必须已解决，或登记具备负责人、期限和关闭产物的 Open Decision | 所有已知冲突必须已解决，或登记具备负责人、期限和关闭产物的 Open Decision | 所有已知冲突必须已解决，或登记具备负责人、期限和关闭产物的 Open Decision | 所有已知冲突必须已解决，或登记具备负责人、期限和关闭产物的 Open Decision
当前状态：6 项 OPEN。G0-01 不满足关闭条件。
Decision ID | Decision | Change Class | Affected Scope | Owner | Due Date | Status | Closure Artifact | Notes
OD-G01-001 | 为全部 Scope Matrix 行指定具名负责人和替补负责人。 | MVP_SCOPE_CHANGE | ALL | Project Manager / Sponsor | 2026-08-25 | OPEN | Named Owner columns completed | 当前仅填 Owner Role，未达到关闭条件。
OD-G01-002 | 确认 GEO Intelligence 正式策略输出是否属于 Commercial MVP，以及最小验收口径。 | MVP_SCOPE_CHANGE | MOD-12 | Product Owner | 2026-08-26 | OPEN | Scope decision + acceptance update | 不阻塞 Walking Skeleton。
OD-G01-003 | 确认 Intervention 与 Effect Validation 的 Commercial MVP 边界。 | MVP_SCOPE_CHANGE | MOD-13 | Product Owner + Domain Architect | 2026-08-27 | OPEN | Versioned intervention acceptance contract | 需区分代码能力完成与行业策略完善。
OD-G01-004 | 确认 Publisher Worker 在 V1 中的状态：DEFERRED 或 MVP-2。 | MVP_SCOPE_CHANGE | RUN-04 | Technical Architect + Product Owner | 2026-08-25 | OPEN | Runtime scope ADR | 当前不作为独立 Gate。
OD-G01-005 | 完成需求方案章节到 Scope ID、Acceptance ID 和 Contract Test ID 的覆盖核对。 | COMPATIBLE_ADDITION | ALL | Business Analyst + QA Lead | 2026-08-28 | OPEN | Requirements coverage report | 用于证明没有模块或验收遗漏。
OD-G01-006 | 冻结正式客户 Mention/Recommendation/Citation KPI 的准入条件。 | BREAKING_CONTRACT | X-19/MOD-14 | Measurement Lead + Product Owner | 2026-08-27 | OPEN | KPI entry ADR + Pack B/C traceability | Basic Report 在此之前只验证 Snapshot 消费。

## Gate Summary
G0-01 Gate Summary | G0-01 Gate Summary | G0-01 Gate Summary | G0-01 Gate Summary | G0-01 Gate Summary | G0-01 Gate Summary
公式驱动的关闭就绪度；当前 Gate 必须保持 OPEN | 公式驱动的关闭就绪度；当前 Gate 必须保持 OPEN | 公式驱动的关闭就绪度；当前 Gate 必须保持 OPEN | 公式驱动的关闭就绪度；当前 Gate 必须保持 OPEN | 公式驱动的关闭就绪度；当前 Gate 必须保持 OPEN | 公式驱动的关闭就绪度；当前 Gate 必须保持 OPEN
OPEN / PENDING REVIEW
Metric | Value
Total scope items | 39
IN | 32
OUT | 2
DEFERRED | 5
Scope decision blanks | 0
Named owner unresolved | 39
Open decisions | 6
Past-due open decisions | 0
G0-01 Exit Checklist
Check | Required Evidence | Current Result | Owner | Status | Close Condition
Scope coverage | All modules + cross-cutting capabilities | 39 items catalogued | Architecture Governance | DRAFT COMPLETE | Review confirms no omitted capability
Scope fields | IN/OUT/DEFERRED, MVP, authority, acceptance, owner | Role owner complete; named owner unresolved | Project Manager | OPEN | Named owners assigned
Authority ADR | Decision-domain authority + conflict rule | ADR-001 PROPOSED | Architecture Governance | PENDING REVIEW | Approved ADR version recorded
Change control | 7 stages + 4 change classes | Drafted | Project Manager | PENDING REVIEW | Approvers and SLAs confirmed
Known conflicts | Resolved or registered with owner/due date | 6 open decisions | Decision Owners | OPEN | All resolved or formally accepted
Gate closure record | Approver, ADR, version, closed at | Not approved | Gate Owner | OPEN | Formal review passes